Warehouse Management System

Man-Days Estimation — Chiffrage

Effort estimate by functionality — code written by Claude Opus 4.8

Scope:  New WMS module for a 3PL (ERP back-office + PWA scanner), integrated into the existing host

Basis:  Bottom-up over 60 build items across 9 phases, calibrated to the agreed mockups

Code author:  Claude Opus 4.8 — man-days are human-led effort (spec, review, integration, test)

Status:  First-cut planning estimate, for client review

Date:  19 June 2026

# 1 · Headline Estimate

Estimated effort with code written by Claude Opus 4.8: ≈ 364 man-days  (planning / P50).

With a 25% contingency for the brownfield-integration unknowns: ≈ 456 man-days  (P80 — the figure to budget to).

For comparison, the same scope hand-coded by a traditional team is ≈ 970–1212 man-days. Using Opus 4.8 removes roughly 62% of the effort — the code is generated; the remaining man-days are human specification, review, host integration, testing and iteration.

All figures are human man-days (≈ one person-day each), not calendar time. Opus 4.8 runtime is a tool cost, not a man-day. See §2 for the method and assumptions.

## Summary by phase

| # | Phase | Items | Traditional md | With Opus 4.8 md |
| --- | --- | --- | --- | --- |
| 0 | Foundation / Kernel | 10 | 122 | 46 |
| 1 | Master Data | 8 | 59.5 | 19 |
| 2 | Goods Reception | 7 | 95 | 37 |
| 3 | Putaway | 3 | 43 | 17 |
| 4 | Stock Visibility & Status | 3 | 30 | 11 |
| 5 | Stock-Out (Outbound) | 8 | 116 | 46 |
| 6 | Inventory Operations | 8 | 108 | 42 |
| 7 | Reports & Visibility | 7 | 68.5 | 24 |
| 8 | Hardening & Closure | 6 | 66 | 24 |
|  | Engineering subtotal | 60 | 708 | 266 |

## Roll-up to the budget figure

| Roll-up | Traditional md | With Opus 4.8 md |
| --- | --- | --- |
| Engineering (sum of all build items) | 708 | 266 |
| + Delivery overhead (PM, system test & UAT, iteration, release) — 37% | 262 | 98 |
| = Project subtotal (P50, planning) | 970 | 364 |
| + Risk contingency (brownfield unknowns) — 25% | 242 | 91 |
| = Total to budget (P80) | 1212 | 456 |
| Optional — PWA offline sync (only if a v1 requirement, decision #5) | + 48 | + 21 |

The optional offline-sync line is excluded from the totals above; add it only if offline scanning is confirmed as a v1 requirement (it is the single largest cost swing).

# 2 · Method & Assumptions

## What a man-day means here

A man-day is one person-day (~8 h) of human engineering effort. Because Claude Opus 4.8 writes the code, that day is spent specifying the change, directing the model, reviewing and correcting what it generates, wiring it into the existing host, testing, and iterating with the client — not hand-typing the bulk of the code. The estimate assumes one engineer fluent in the host stack (.NET Core 3.1 / Angular 14 / SQL Server 2014) and skilled at driving Opus 4.8.

## How each figure is built

Every build item is sized on the project estimation guide’s complexity tiers (which sum backend, database, ERP UI, PWA UI and test effort). That yields a traditional human figure. An Opus-4.8 acceleration factor is then applied per tier — larger for boilerplate (CRUD), smaller for the host-integration and engine work where human review and debugging dominate:

| Tier | Profile | Trad. md | × Opus | Opus md |
| --- | --- | --- | --- | --- |
| S | CRUD master over the generic base service | 4 | 0.30 | 1.0 |
| S–M | small CRUD with a little logic | 6.5 | 0.33 | 2.0 |
| M | CRUD + non-trivial rules / one guard | 9 | 0.35 | 3.0 |
| M–L | multi-step, some cross-cutting calls | 13 | 0.38 | 5.0 |
| L | multi-step dual-channel flow, 3+ cross-cutting calls | 17 | 0.40 | 7.0 |
| XL | engine / orchestration, heavy edge cases | 28 | 0.45 | 12.5 |

Tier baselines are calibrated against the project’s estimation guide and the completed mockups as a reference class.

## What is included

- Backend domain + services + APIs, database schema & migrations (SQL Server 2014), ERP screens (Angular/NgRx/Kendo), PWA scanner screens, and per-item tests.

- Integration into the existing host — Swagger client regeneration, gateway routing, DI wiring, identity/role reuse.

- Delivery overhead — project management, system & integration testing, client UAT support, environment/CI-CD, SQL migration runbook and release.

- A risk contingency keyed to the brownfield unknowns (SQL 2014 child-table modelling, the shared Auth module, .NET 3.1 / Angular 14 tooling, the open decisions).

## What is excluded (price separately)

- Client portal and billing (out of v1 by decision).

- Label-printer / hardware integration and procurement (the mock prints client-side; production needs a print service).

- Infrastructure & hosting, data migration from any legacy WMS, end-user training & change management, and post-go-live support / SLA.

## Key assumptions

- The functional scope and UX are locked — the Phase-2 mockups and the docs/ specs act as the specification, which removes most analysis/design effort (already reflected in the factors).

- Brownfield build: a new WMS module inside the existing ERP, reusing identity, data-access, gateway and UI kit.

- Online-only PWA for v1. Offline scanning (decision #5) is the separate optional line.

- Stay on the host runtimes (.NET Core 3.1 / Angular 14 / SQL Server 2014); EF migrations for schema; WMS-side tenant scoping.

- One delivery team. Figures are human man-days, not elapsed calendar time (parallelism shortens the calendar, not the man-days).

# 3 · Detail by Phase & Functionality

One line per build item. "Delivers" names the function or page(s) produced. Traditional = hand-coded human days; Opus 4.8 = human-led days with the model writing the code.

## Phase 0 · Foundation / Kernel

One-time enabling platform — module, schema, and the shared services every process reuses.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P00-S01 | Backend module skeleton (7 projects) + DI / gateway route / Swagger client pipeline; Angular ERP + PWA project shells & routing | M | 9 | 3 |
| P00-S02 | SQL Server 2014 schema foundation, EF DbContext, audit-ledger table, migrations + seed from the mock dataset | L | 17 | 7 |
| P00-S03 | Tenant / site scoping service + WMS role/claim integration (touches the shared Auth module) | L | 17 | 7 |
| P00-S04 | Stock-ledger service — append-only transaction log, written in-transaction by every action | M | 9 | 3 |
| P00-S05 | Freeze service — the cross-screen frozen-scope guard | M | 9 | 3 |
| P00-S06 | Capacity + segregation service — single source of truth for every bin write | M | 9 | 3 |
| P00-S07 | Allocation engine core — FEFO / FIFO + reservation-aware availability | L | 17 | 7 |
| P00-S08 | Reason-code service + approval / maker-checker framework | M | 9 | 3 |
| P00-S09 | Work-item assignment facet (My-tasks / claim) + tracking-flag (lot/expiry/serial) plumbing | M | 9 | 3 |
| P00-S10 | PWA shell — scan engine (camera / ZXing / manual / list), service worker, shared models & API client | L | 17 | 7 |
|  | Phase 0 subtotal |  | 122 | 46 |

## Phase 1 · Master Data

Mostly the CRUD recipe over the Phase-0 base classes — highly parallel.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P01-S01 | Clients (+ back-order policy), Suppliers, Carriers, Consignees | S–M | 6.5 | 2 |
| P01-S02 | Sites (+ addressing levels, storage areas), Locations (+ capacity, area) | M | 9 | 3 |
| P01-S03 | Products (+ tracking flags, category, weight, preferred storage), Categories, UoM | M | 9 | 3 |
| P01-S04 | Packaging — shared templates + per-product packaging with per-level barcodes | M | 9 | 3 |
| P01-S05 | Reason Codes master (all domains) | S | 4 | 1 |
| P01-S06 | Users + WMS roles/rights + client/site scope + client–user mapping | M | 9 | 3 |
| P01-S07 | PWA lookups (location, product) — read-only | S | 4 | 1 |
| P01-S08 | Bulk CSV import (products, locations) | M | 9 | 3 |
|  | Phase 1 subtotal |  | 59.5 | 19 |

## Phase 2 · Goods Reception

First stock-creating process — ASN → receive → inspect → GRN, minting LPNs. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P02-S01 | ASN management — CRUD, lines, derived open / partial / closed status | M | 9 | 3 |
| P02-S02 | Receive against ASN + blind → mint LPNs, LPN split (per-each / per-pack), close-short, wrong-client guard | L | 17 | 7 |
| P02-S03 | Mixed-pallet build (aggregate LPN + manifest label) + decomposition hand-off to Putaway | L | 17 | 7 |
| P02-S04 | Inspection — quantity-based partial accept/reject, dispositions, reason codes | L | 17 | 7 |
| P02-S05 | GRN — Goods Received Note (document / print, one per receipt) | M | 9 | 3 |
| P02-S06 | Labels / reprint (LPN + pallet, recovery by ASN / recent, audited) | M | 9 | 3 |
| P02-S07 | Reception edge cases — refuse-at-door, over-receipt approval, duplicate / damaged / expired guards, cold-chain | L | 17 | 7 |
|  | Phase 2 subtotal |  | 95 | 37 |

## Phase 3 · Putaway

Directed slotting into bins, enforcing capacity / segregation / freeze. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P03-S01 | Single-LPN directed putaway — ranked bins (home→consolidate→category→open), guards, partial split | L | 17 | 7 |
| P03-S02 | Mixed-pallet decomposition — operator-chosen order → child LPNs | L | 17 | 7 |
| P03-S03 | Damage-found reject, overflow-park, resume / partial-progress visibility | M | 9 | 3 |
|  | Phase 3 subtotal |  | 43 | 17 |

## Phase 4 · Stock Visibility & Status

The read model + status engine that Stock-Out and Reports both depend on.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P04-S01 | Stock-on-hand / availability read model + query API (the hot path for outbound & reports) | L | 17 | 7 |
| P04-S02 | Stock Status screen + reason-coded status-change engine | M | 9 | 3 |
| P04-S03 | Expose blocked / frozen / expiry / in-transit flags consistently across every stock payload | S | 4 | 1 |
|  | Phase 4 subtotal |  | 30 | 11 |

## Phase 5 · Stock-Out (Outbound)

The most complex process — orders → allocation → pick/dispatch → delivery notes. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P05-S01 | Outbound orders — CRUD, lines, ship-to consignee, full-stock-out, cancel order / line, status flow | M–L | 13 | 5 |
| P05-S02 | Allocation surface — FEFO/FIFO, reservation-aware, short-pick, manual override | L | 17 | 7 |
| P05-S03 | Pick / Dispatch (classic) — scan-confirm, serials-on-issue, carrier + proof-of-load, Delivery Note | L | 17 | 7 |
| P05-S04 | Express Fulfil — one-pass allocate→pick→dispatch, role-gated | L | 17 | 7 |
| P05-S05 | Back-order vs short-close + multi-shipment delivery notes | M | 9 | 3 |
| P05-S06 | Ad-hoc / emergency dispatch — governance gate, role-gated + back-office approval queue | L | 17 | 7 |
| P05-S07 | Return-to-vendor / client — non-consignee outbound | M | 9 | 3 |
| P05-S08 | PWA pick / dispatch + ad-hoc + RTV parity | L | 17 | 7 |
|  | Phase 5 subtotal |  | 116 | 46 |

## Phase 6 · Inventory Operations

In-warehouse stock operations incl. the freeze workflow; each card largely standalone.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P06-S01 | Move — intra-site relocation, partial split, guards | M–L | 13 | 5 |
| P06-S02 | Transfer — inter-site ship → in-transit → receive | L | 17 | 7 |
| P06-S03 | Cycle Count — multi-location sheet → approve corrects stock; found / missing | L | 17 | 7 |
| P06-S04 | Physical Inventory — freeze → count → post → unfreeze | L | 17 | 7 |
| P06-S05 | Adjustments (qty) + Corrections (attributes) — approval-gated | M | 9 | 3 |
| P06-S06 | Repack / split / merge / re-kit — genealogy + balance guard | L | 17 | 7 |
| P06-S07 | Returns / put-back — dispositions (restock / via-putaway / quarantine) | M | 9 | 3 |
| P06-S08 | Disposal / Scrap — approval-gated, terminal, maker-checker | M | 9 | 3 |
|  | Phase 6 subtotal |  | 108 | 42 |

## Phase 7 · Reports & Visibility

Read-only over the stock read model + the ledger. ERP only.

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P07-S01 | Stock on Hand | M | 9 | 3 |
| P07-S02 | Transaction History / stock ledger | M | 9 | 3 |
| P07-S03 | Expiry & Aging | S–M | 6.5 | 2 |
| P07-S04 | Inbound & Outbound activity | M | 9 | 3 |
| P07-S05 | Variance & Bin / Location Utilization | M | 9 | 3 |
| P07-S06 | Lot / Serial Traceability + Stock Card / Product Ledger | L | 17 | 7 |
| P07-S07 | Client Stock Statement | M | 9 | 3 |
|  | Phase 7 subtotal |  | 68.5 | 24 |

## Phase 8 · Hardening & Closure

Production-grade non-functionals + carry-overs. (PWA offline sync is a separate optional line.)

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P08-S01 | Export (CSV / Excel) across all reports | M | 9 | 3 |
| P08-S02 | Performance pass — indexes, query tuning, load tests on SQL 2014, grid paging | M–L | 13 | 5 |
| P08-S03 | Security review — server-side scoping on every endpoint, role matrix, authz tests | L | 17 | 7 |
| P08-S04 | Audit completeness — immutable ledger + before/after snapshots, reprint / override auditing | M | 9 | 3 |
| P08-S05 | Operations dashboard wired to live rollups | M | 9 | 3 |
| P08-S07 | Carry-over alignment sweep — shared capacity service, dispatch-txn parity, etc. | M | 9 | 3 |
|  | Phase 8 subtotal |  | 66 | 24 |

## Optional — conditional on decision #5

| Item | Delivers | Tier | Trad. md | Opus md |
| --- | --- | --- | --- | --- |
| P08-S06 | PWA offline sync — IndexedDB queue, sync-on-reconnect, conflict resolution (only if offline scanning is a v1 requirement — open decision #5) | XL | 28 | 12.5 |

# 4 · Overhead, Risk & Adjusting the Estimate

## Delivery overhead

Applied as a percentage of the engineering subtotal (it scales with the work):

| Overhead component | % | Trad. md | Opus md |
| --- | --- | --- | --- |
| System test, integration & UAT | 12% | 85 | 31.9 |
| Project management & coordination | 12% | 85 | 31.9 |
| Client review & iteration loops | 8% | 56.6 | 21.3 |
| Environment, CI/CD, SQL migration & release | 5% | 35.4 | 13.3 |
| Total overhead | 37% | 262 | 98 |

## Risk contingency

A flat 25% contingency takes the planning (P50) figure to a budget (P80) figure. The risk is concentrated in the brownfield integration — modelling the mock’s nested data as SQL Server 2014 child tables, extending the shared Auth module for tenant/site scoping, the EOL .NET Core 3.1 / Angular 14 tooling, and resolving the five open integration decisions. A team may key the buffer per item instead (+15% known · +30% open question · +50% shared-module / unknown).

## How to adjust

- The estimate is a model with four levers: the per-tier baseline days, the Opus-4.8 factor per tier, the overhead %, and the risk %. Change any one and the totals re-flow.

- The Opus-4.8 factors (0.30–0.45) are the central judgement. If early build items run faster or slower than assumed, recalibrate them after the first 2–3 items and the rest of the estimate follows.

- A line-by-line, adjustable spreadsheet version (one row per build item, with the levers on an assumptions sheet) is the natural next artifact if you want to tune the numbers interactively.

This is a first-cut, top-down-calibrated estimate for planning. It is not a fixed-price quotation; the figure to budget against is the P80 total in §1.