Warehouse Management System

Man-Days Estimation — Chiffrage

Optimistic scenario — senior developer (× 5/8)

Code written by Claude Opus 4.8, implemented by an experienced senior developer

Scope:  New WMS module for a 3PL (ERP back-office + PWA scanner), integrated into the existing host

Basis:  Bottom-up over 60 build items across 9 phases, calibrated to the agreed mockups

Scenario:  Optimistic — the baseline Opus 4.8 estimate × 5/8 (0.625) for a senior developer

Status:  Optimistic planning estimate, for client review

Date:  19 June 2026

# 1 · Headline Estimate

Estimated effort — Claude Opus 4.8 with a senior developer (optimistic): ≈ 229 man-days  (planning / P50).

With a 25% contingency for the brownfield-integration unknowns: ≈ 287 man-days  (P80 — the figure to budget to).

This optimistic scenario applies a 5/8 (0.625) senior-developer productivity factor to the baseline Opus 4.8 estimate of ≈ 364 / ≈ 456 man-days (P50 / P80), reflecting an experienced senior developer implementing the application.

For comparison, the same scope hand-coded by a traditional team is ≈ 970–1212 man-days. Opus 4.8 with a senior developer removes roughly 76% of that effort — the code is generated; the remaining man-days are human specification, review, host integration, testing and iteration, at a senior pace.

All figures are human man-days (≈ one person-day each), not calendar time. Opus 4.8 runtime is a tool cost, not a man-day. See §2 for the method and assumptions.

## Summary by phase

| # | Phase | Items | Traditional md | Opus 4.8 + Sr md |
| --- | --- | --- | --- | --- |
| 0 | Foundation / Kernel | 10 | 122 | 29 |
| 1 | Master Data | 8 | 59.5 | 12 |
| 2 | Goods Reception | 7 | 95 | 23.3 |
| 3 | Putaway | 3 | 43 | 10.7 |
| 4 | Stock Visibility & Status | 3 | 30 | 6.9 |
| 5 | Stock-Out (Outbound) | 8 | 116 | 28.9 |
| 6 | Inventory Operations | 8 | 108 | 26.4 |
| 7 | Reports & Visibility | 7 | 68.5 | 15.2 |
| 8 | Hardening & Closure | 6 | 66 | 15.1 |
|  | Engineering subtotal | 60 | 708 | 167.5 |

## Roll-up to the budget figure

| Roll-up | Traditional md | Opus 4.8 + Sr md |
| --- | --- | --- |
| Engineering (sum of all build items) | 708 | 167.5 |
| + Delivery overhead (PM, system test & UAT, iteration, release) — 37% | 262 | 62 |
| = Project subtotal (P50, planning) | 970 | 229 |
| + Risk contingency (brownfield unknowns) — 25% | 242 | 57 |
| = Total to budget (P80) | 1212 | 287 |
| Optional — PWA offline sync (only if a v1 requirement, decision #5) | + 48 | + 13 |

The optional offline-sync line is excluded from the totals above; add it only if offline scanning is confirmed as a v1 requirement (it is the single largest cost swing).

# 2 · Method & Assumptions

## What a man-day means here

A man-day is one person-day (~8 h) of human engineering effort. Because Claude Opus 4.8 writes the code, that day is spent specifying the change, directing the model, reviewing and correcting what it generates, wiring it into the existing host, testing, and iterating with the client — not hand-typing the bulk of the code. This optimistic scenario further assumes an experienced senior developer fluent in the host stack (.NET Core 3.1 / Angular 14 / SQL Server 2014), who reviews, integrates and decides faster than an average engineer.

## How each figure is built

Every build item is sized on the project estimation guide’s complexity tiers (which sum backend, database, ERP UI, PWA UI and test effort) to give a traditional human figure. An Opus-4.8 acceleration factor is applied per tier to get the baseline Opus figure; this optimistic scenario then multiplies that by a 5/8 (0.625) senior-developer factor:

| Tier | Profile | Trad. md | Opus 4.8 md | × 5/8 | Final md |
| --- | --- | --- | --- | --- | --- |
| S | CRUD master over the generic base service | 4 | 1.0 | 0.625 | 0.6 |
| S–M | small CRUD with a little logic | 6.5 | 2.0 | 0.625 | 1.3 |
| M | CRUD + non-trivial rules / one guard | 9 | 3.0 | 0.625 | 1.9 |
| M–L | multi-step, some cross-cutting calls | 13 | 5.0 | 0.625 | 3.1 |
| L | multi-step dual-channel flow, 3+ cross-cutting calls | 17 | 7.0 | 0.625 | 4.4 |
| XL | engine / orchestration, heavy edge cases | 28 | 12.5 | 0.625 | 7.8 |

“Opus 4.8 md” are the figures from the standard estimate; “Final md” = those × 5/8, rounded per item. Tier baselines are calibrated against the project’s estimation guide and the completed mockups as a reference class.

## What is included

- Backend domain + services + APIs, database schema & migrations (SQL Server 2014), ERP screens (Angular/NgRx/Kendo), PWA scanner screens, and per-item tests.

- Integration into the existing host — Swagger client regeneration, gateway routing, DI wiring, identity/role reuse.

- Delivery overhead — project management, system & integration testing, client UAT support, environment/CI-CD, SQL migration runbook and release.

- A risk contingency keyed to the brownfield unknowns (SQL 2014 child-table modelling, the shared Auth module, .NET 3.1 / Angular 14 tooling, the open decisions).

## What is excluded (price separately)

- Client portal and billing (out of v1 by decision).

- Label-printer / hardware integration and procurement (the mock prints client-side; production needs a print service).

- Infrastructure & hosting, data migration from any legacy WMS, end-user training & change management, and post-go-live support / SLA.

## Key assumptions

- Optimistic scenario: an experienced senior developer (the 5/8 factor). Treat the standard Opus 4.8 estimate (≈ 364 / ≈ 456 md) as the more conservative companion figure.

- The functional scope and UX are locked — the Phase-2 mockups and the docs/ specs act as the specification, which removes most analysis/design effort (already reflected in the factors).

- Brownfield build: a new WMS module inside the existing ERP, reusing identity, data-access, gateway and UI kit.

- Online-only PWA for v1. Offline scanning (decision #5) is the separate optional line.

- Stay on the host runtimes (.NET Core 3.1 / Angular 14 / SQL Server 2014); EF migrations for schema; WMS-side tenant scoping.

- One delivery team. Figures are human man-days, not elapsed calendar time (parallelism shortens the calendar, not the man-days).

# 3 · Detail by Phase & Functionality

One line per build item. "Delivers" names the function or page(s) produced. Traditional = hand-coded human days; Opus 4.8 + Sr = senior-developer days with the model writing the code (the baseline Opus figure × 5/8).

## Phase 0 · Foundation / Kernel

One-time enabling platform — module, schema, and the shared services every process reuses.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P00-S01 | Backend module skeleton (7 projects) + DI / gateway route / Swagger client pipeline; Angular ERP + PWA project shells & routing | M | 9 | 1.9 |
| P00-S02 | SQL Server 2014 schema foundation, EF DbContext, audit-ledger table, migrations + seed from the mock dataset | L | 17 | 4.4 |
| P00-S03 | Tenant / site scoping service + WMS role/claim integration (touches the shared Auth module) | L | 17 | 4.4 |
| P00-S04 | Stock-ledger service — append-only transaction log, written in-transaction by every action | M | 9 | 1.9 |
| P00-S05 | Freeze service — the cross-screen frozen-scope guard | M | 9 | 1.9 |
| P00-S06 | Capacity + segregation service — single source of truth for every bin write | M | 9 | 1.9 |
| P00-S07 | Allocation engine core — FEFO / FIFO + reservation-aware availability | L | 17 | 4.4 |
| P00-S08 | Reason-code service + approval / maker-checker framework | M | 9 | 1.9 |
| P00-S09 | Work-item assignment facet (My-tasks / claim) + tracking-flag (lot/expiry/serial) plumbing | M | 9 | 1.9 |
| P00-S10 | PWA shell — scan engine (camera / ZXing / manual / list), service worker, shared models & API client | L | 17 | 4.4 |
|  | Phase 0 subtotal |  | 122 | 29 |

## Phase 1 · Master Data

Mostly the CRUD recipe over the Phase-0 base classes — highly parallel.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P01-S01 | Clients (+ back-order policy), Suppliers, Carriers, Consignees | S–M | 6.5 | 1.3 |
| P01-S02 | Sites (+ addressing levels, storage areas), Locations (+ capacity, area) | M | 9 | 1.9 |
| P01-S03 | Products (+ tracking flags, category, weight, preferred storage), Categories, UoM | M | 9 | 1.9 |
| P01-S04 | Packaging — shared templates + per-product packaging with per-level barcodes | M | 9 | 1.9 |
| P01-S05 | Reason Codes master (all domains) | S | 4 | 0.6 |
| P01-S06 | Users + WMS roles/rights + client/site scope + client–user mapping | M | 9 | 1.9 |
| P01-S07 | PWA lookups (location, product) — read-only | S | 4 | 0.6 |
| P01-S08 | Bulk CSV import (products, locations) | M | 9 | 1.9 |
|  | Phase 1 subtotal |  | 59.5 | 12 |

## Phase 2 · Goods Reception

First stock-creating process — ASN → receive → inspect → GRN, minting LPNs. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P02-S01 | ASN management — CRUD, lines, derived open / partial / closed status | M | 9 | 1.9 |
| P02-S02 | Receive against ASN + blind → mint LPNs, LPN split (per-each / per-pack), close-short, wrong-client guard | L | 17 | 4.4 |
| P02-S03 | Mixed-pallet build (aggregate LPN + manifest label) + decomposition hand-off to Putaway | L | 17 | 4.4 |
| P02-S04 | Inspection — quantity-based partial accept/reject, dispositions, reason codes | L | 17 | 4.4 |
| P02-S05 | GRN — Goods Received Note (document / print, one per receipt) | M | 9 | 1.9 |
| P02-S06 | Labels / reprint (LPN + pallet, recovery by ASN / recent, audited) | M | 9 | 1.9 |
| P02-S07 | Reception edge cases — refuse-at-door, over-receipt approval, duplicate / damaged / expired guards, cold-chain | L | 17 | 4.4 |
|  | Phase 2 subtotal |  | 95 | 23.3 |

## Phase 3 · Putaway

Directed slotting into bins, enforcing capacity / segregation / freeze. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P03-S01 | Single-LPN directed putaway — ranked bins (home→consolidate→category→open), guards, partial split | L | 17 | 4.4 |
| P03-S02 | Mixed-pallet decomposition — operator-chosen order → child LPNs | L | 17 | 4.4 |
| P03-S03 | Damage-found reject, overflow-park, resume / partial-progress visibility | M | 9 | 1.9 |
|  | Phase 3 subtotal |  | 43 | 10.7 |

## Phase 4 · Stock Visibility & Status

The read model + status engine that Stock-Out and Reports both depend on.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P04-S01 | Stock-on-hand / availability read model + query API (the hot path for outbound & reports) | L | 17 | 4.4 |
| P04-S02 | Stock Status screen + reason-coded status-change engine | M | 9 | 1.9 |
| P04-S03 | Expose blocked / frozen / expiry / in-transit flags consistently across every stock payload | S | 4 | 0.6 |
|  | Phase 4 subtotal |  | 30 | 6.9 |

## Phase 5 · Stock-Out (Outbound)

The most complex process — orders → allocation → pick/dispatch → delivery notes. Dual-channel.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P05-S01 | Outbound orders — CRUD, lines, ship-to consignee, full-stock-out, cancel order / line, status flow | M–L | 13 | 3.1 |
| P05-S02 | Allocation surface — FEFO/FIFO, reservation-aware, short-pick, manual override | L | 17 | 4.4 |
| P05-S03 | Pick / Dispatch (classic) — scan-confirm, serials-on-issue, carrier + proof-of-load, Delivery Note | L | 17 | 4.4 |
| P05-S04 | Express Fulfil — one-pass allocate→pick→dispatch, role-gated | L | 17 | 4.4 |
| P05-S05 | Back-order vs short-close + multi-shipment delivery notes | M | 9 | 1.9 |
| P05-S06 | Ad-hoc / emergency dispatch — governance gate, role-gated + back-office approval queue | L | 17 | 4.4 |
| P05-S07 | Return-to-vendor / client — non-consignee outbound | M | 9 | 1.9 |
| P05-S08 | PWA pick / dispatch + ad-hoc + RTV parity | L | 17 | 4.4 |
|  | Phase 5 subtotal |  | 116 | 28.9 |

## Phase 6 · Inventory Operations

In-warehouse stock operations incl. the freeze workflow; each card largely standalone.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P06-S01 | Move — intra-site relocation, partial split, guards | M–L | 13 | 3.1 |
| P06-S02 | Transfer — inter-site ship → in-transit → receive | L | 17 | 4.4 |
| P06-S03 | Cycle Count — multi-location sheet → approve corrects stock; found / missing | L | 17 | 4.4 |
| P06-S04 | Physical Inventory — freeze → count → post → unfreeze | L | 17 | 4.4 |
| P06-S05 | Adjustments (qty) + Corrections (attributes) — approval-gated | M | 9 | 1.9 |
| P06-S06 | Repack / split / merge / re-kit — genealogy + balance guard | L | 17 | 4.4 |
| P06-S07 | Returns / put-back — dispositions (restock / via-putaway / quarantine) | M | 9 | 1.9 |
| P06-S08 | Disposal / Scrap — approval-gated, terminal, maker-checker | M | 9 | 1.9 |
|  | Phase 6 subtotal |  | 108 | 26.4 |

## Phase 7 · Reports & Visibility

Read-only over the stock read model + the ledger. ERP only.

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P07-S01 | Stock on Hand | M | 9 | 1.9 |
| P07-S02 | Transaction History / stock ledger | M | 9 | 1.9 |
| P07-S03 | Expiry & Aging | S–M | 6.5 | 1.3 |
| P07-S04 | Inbound & Outbound activity | M | 9 | 1.9 |
| P07-S05 | Variance & Bin / Location Utilization | M | 9 | 1.9 |
| P07-S06 | Lot / Serial Traceability + Stock Card / Product Ledger | L | 17 | 4.4 |
| P07-S07 | Client Stock Statement | M | 9 | 1.9 |
|  | Phase 7 subtotal |  | 68.5 | 15.2 |

## Phase 8 · Hardening & Closure

Production-grade non-functionals + carry-overs. (PWA offline sync is a separate optional line.)

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P08-S01 | Export (CSV / Excel) across all reports | M | 9 | 1.9 |
| P08-S02 | Performance pass — indexes, query tuning, load tests on SQL 2014, grid paging | M–L | 13 | 3.1 |
| P08-S03 | Security review — server-side scoping on every endpoint, role matrix, authz tests | L | 17 | 4.4 |
| P08-S04 | Audit completeness — immutable ledger + before/after snapshots, reprint / override auditing | M | 9 | 1.9 |
| P08-S05 | Operations dashboard wired to live rollups | M | 9 | 1.9 |
| P08-S07 | Carry-over alignment sweep — shared capacity service, dispatch-txn parity, etc. | M | 9 | 1.9 |
|  | Phase 8 subtotal |  | 66 | 15.1 |

## Optional — conditional on decision #5

| Item | Delivers | Tier | Trad. md | Opus+Sr md |
| --- | --- | --- | --- | --- |
| P08-S06 | PWA offline sync — IndexedDB queue, sync-on-reconnect, conflict resolution (only if offline scanning is a v1 requirement — open decision #5) | XL | 28 | 7.8 |

# 4 · Overhead, Risk & Adjusting the Estimate

## Delivery overhead

Applied as a percentage of the engineering subtotal (it scales with the work):

| Overhead component | % | Trad. md | Opus+Sr md |
| --- | --- | --- | --- |
| System test, integration & UAT | 12% | 85 | 20.1 |
| Project management & coordination | 12% | 85 | 20.1 |
| Client review & iteration loops | 8% | 56.6 | 13.4 |
| Environment, CI/CD, SQL migration & release | 5% | 35.4 | 8.4 |
| Total overhead | 37% | 262 | 62 |

## Risk contingency

A flat 25% contingency takes the planning (P50) figure to a budget (P80) figure. The risk is concentrated in the brownfield integration — modelling the mock’s nested data as SQL Server 2014 child tables, extending the shared Auth module for tenant/site scoping, the EOL .NET Core 3.1 / Angular 14 tooling, and resolving the five open integration decisions. Note that an optimistic productivity factor and a thin contingency compound: if the senior-developer pace does not hold, this scenario has less cushion than the standard estimate.

## How to adjust

- The estimate is a model with five levers: the per-tier baseline days, the Opus-4.8 factor per tier, the senior-developer factor (here 5/8), the overhead %, and the risk %. Change any one and the totals re-flow.

- The senior-developer factor (5/8) is the optimistic lever in this version. Setting it to 1.0 returns the standard Opus 4.8 estimate (≈ 364 / ≈ 456 md); a value between the two brackets the realistic range.

- Recalibrate the factors after the first 2–3 real build items — the actual senior pace on this host will quickly show whether 5/8 holds, and the rest of the estimate follows.

- A line-by-line, adjustable spreadsheet version (one row per build item, with all the levers on an assumptions sheet) is the natural next artifact if you want to tune the numbers interactively.

This is an optimistic, first-cut planning estimate. It is not a fixed-price quotation; budget against the P80 total in §1, and keep the standard Opus 4.8 estimate as the more conservative companion.